## Slide 1: Cradle Risk Management
Features and Integration
RR023/02: January 2023

## Slide 2: Contents
  Risk Management
  Risk Management Plan
  Representation of Risks
  Risk Attributes
  Working with Risks
  Risk Profiles
  RISK Licence
  Summary

## Slide 3: Risk Management 1
A risk is an event which, if it occurs, has an effect on project objective(s), such as cost, completion, timescales, or preventing injury to persons or environmental damage
Risk management is the name for activities to:
  Identify and characterise risks and define their priority / severity
  Define and implement means to mitigate or eliminate risks
  Review the risks and mitigations for continued accuracy and completeness
  Review the mitigations for continued relevance and effectiveness
In a Cradle database, risks are often:
  A hierarchy of one or more risk registers
    Containing the risks
  Each risk is often linked to:
    Its sources, such as requirements
    Its effect, such as on SBS or functions
Risks
Risks
Risks
Requirements
Requirements
Requirements
SBS
SBS
SBS

## Slide 4: Risk Management Plan 2
The first risk management task
Defines:
  Principles and basis of all risk management work
  Representation of risks and related data in Cradle – part of the schema
Includes:
  Methodology, becomes Cradle risk schema and procedures surrounding it, such as:
    Sources for finding risks and other data (such as user requirements, ConOps)
    Risk identification methods (interviews with experts, past projects…)
    Risk analysis methods (qualitative and/or quantitative)
    Risk sources, items that can originate risks
    Risk impacts, items that can be affected / impacted by risks
    Representation of mitigations, as attribute or linked items
    Allocation of risk responsibilities, to people / groups, as attribute / linked items
  Budget, resources and responsibilities for risk activities

## Slide 5: Risk Management Plan: 2
  Timing, schedules for risk definition, review and monitoring
  Risk categorisation, the types or groups of risks
    Typically defines structure of risk register(s)
    Creates the risk hierarchy = Risk Breakdown Structure (RBS)
  Likelihood and impact:
    Risk likelihood values and their probabilities – part of the schema
    Risk consequence values – part of the schema
    Risk magnitude / priority / severity values – part of the schema
    Risk Assessment Matrices (RAMs) to set risk priority from its likelihood and consequence. Is stored in risk’s frame and inherited by the risk’s children.

## Slide 6: Risk Management Plan: 3
  Risk mitigation strategies that are allowed (part of the schema), such as:
    Accept The project will accept that the risk may occur and will deal with its consequences if it does occur
    Avoid The project will take action to prevent the risk occurring, the extent will be determined by the magnitude / priority / severity of the risk
    Transfer The project transfers the risk to another party, for example purchasing insurance
    Reduce The project will take some action to reduce the likelihood of the risk occurring but to a lesser extent than Avoid, the extent will be determined by the magnitude / priority / severity of the risk
and the policies for their use and how they are to be mitigated

## Slide 7: Risk Management Plan: 4
  Risk reporting:
    Types of reports, such as risk registers and risk profiles
    Recipients
    Frequency
    Formats, including tabular, document and graphical
  Monitoring and tracking
    Which people / groups can be given responsibility for risks
    Frequency and methods of:
      Identifying new risks
      Validating existing risks
      Risk analysis
      Validating risk mitigation strategies and actions
    Methods to track risk management activity
    Methods and frequency of audits of the risk management activity
    Governance of the risk management activity, including audits

## Slide 8: Representation of Risks 3
Each risk is an item in the database
You decide how risk mitigations will be managed, either:
  As an attribute of the risk:
  As items linked to the risk:
    Perhaps shared between risks
Mitigation Strategy
RISK
Mitigation
Mitigation Strategy
RISK
MITIGATION
MITIGATION
Mitigation Strategy
RISK
MITIGATION

## Slide 9: Representation of Risks: 2
Risks are usually in hierarchies, a RBS, so they have parent/child links
You can link risks to their source / cause / origin:
  Typically needs or requirements, or both
You can link risks to items affected if the risk occurs
  Typically SBS items or functions in a model
Typical schema for risk management (part of overall schema) is:
RISK
REQUIREMENT
MITIGATION
SBS
HAS CHILD
HAS CHILD
HAS CHILD
IS MITIGATED BY
IS CAUSED BY
HAS EFFECT ON

## Slide 10: Risk Attributes 4
Risk attributes are all user-defined, in two groups:
  Optional attributes, chosen for your risk management process
  Required attributes needed for Cradle’s risk analyses and risk profiles
We recommend that risks are auto-numbered
Suggested optional attributes are:
  An ID, for a hierarchical number that positions the risk in the RBS
  A name, optional but helpful
  A statement or description that summarises the risk
  Details of the factors that contribute to the risk
  Details of the effects of the risk, if it occurs
  Details of the mitigation of the risk, if mitigations are not held separately
  A subject (such as build, timing, performance, resource…), so risks can be grouped
  A rationale for the risk, why it is as it is and/or why it is not something else
  Some notes for the risk

## Slide 11: Risk Attributes: 2
Required attributes needed for risk operations are defined in the schema (typically as category codes) and identified in the Risk Settings so Cradle knows the values to use:

## Slide 12: Risk Attributes: 3
  Risk category, groups of risks, typically represented as a hierarchy, such as:
Risks
Commercial
Functional
Health & Safety
External
Group
Group
Risk
Risk
Risk
Risk
Risk
Risk
Risk
Group
Group
Risk
Risk
Risk
Risk
Risk

## Slide 13: Risk Attributes: 4
  Likelihood, how likely is the risk, set of user-defined values, each with a probability
    From the Likelihood section in the risk management plan
    The values for one axis of a Risk Assessment Matrix (RAM)
    Probability specified as N and processed as 1/N
    So: 1 = certainty 100 = 1/100 = 1% chance
  Consequence, how serious is the risk if it occurs, a set of user defined values
    Based on the Consequences section in the risk management plan
    The values for the second axis of a RAM

## Slide 14: Risk Attributes: 5
  Magnitude, the priority or severity of the risk, a set of user defined values:
    These values are very important
    They define the size / scope / importance of the actions required by the project in response to the risk
    Derived from the corresponding section in the risk management plan
    Are the values of the cells in all RAM(s)
    Set automatically by lookup in a RAM for a risk’s likelihood and consequence
    The RAM used is either:
      The risk’s own RAM
      The RAM inherited by the risk from its parent, grandparent…
    Is read-only, it is a calculated value
  Hierarchy link type, the type of cross reference to be followed upwards to find a RAM in an ancestor risk in the risk register / RBS
  Start Date and End Date, the period when the risk exists, used in risk profiles

## Slide 15: Risk Attributes: 6
  Risk Assessment Matrix, defines the risk magnitude / priority / severity value for all possible combinations of risk likelihood and consequence:
    If a risk has no RAM, it inherits the RAM in its parent risk, or its parent, or its parent… until a RAM is found or the top of the RBS is reached
    Likely that different RAMs will be needed for different risk subjects:
      Risks related to human injury have far fewer low priority values

## Slide 16: Risk Attributes: 7
  Responsibility, who is responsible for managing the risk, list of user-defined values
  Review Date, a date when the risk should be reviewed according to the Timing and Monitoring and Tracking sections of the risk management plan
    Can be used to filter risks needing review
  Mitigation, the mitigation strategy for the risk, a set of user-defined values based on the Mitigation section of the risk management plan
  Mitigation Details, either In Frame or As Item:
    If In Frame, then:
      Mitigation Frame, which frame stores the mitigation details for the risk
    If As Item, then:
      Mitigation Item Type, item type storing the risk’s mitigation details
      Mitigation Link Type, type of cross reference between the risk and mitigation

## Slide 17: Working with Risks 5
All risk information is held as items:
  Such as RISK, MITIGATION, NEED, REQUIREMENT, SBS, FUNCTION
So everything in Cradle for items will also apply to risks:
  Access control uses your user-defined access control rules
  Operations use standard Cradle mechanisms, such as:
    Queries, including nested queries and parametric queries
    Views and display Styles, including linked item views, nested tables, view commands, pivot tables, matrices, graphs, metrics, dashboards of KPIs
    Forms including user-defined commands
    Making new items with New, New Child, New Sibling, New Hierarchy
    Copy, Delete, Properties, Split, Merge, Reorder
    User-defined workflows, Advance, baselines, formal changes in Cradle’s CM
  Risks can be captured from source documents
  All risk information can be published in reports and documents
  Risks can be accessed through the API and WSI

## Slide 18: Working with Risks: 2
Benefits:
  Users work with risks in same way as all other information
  No need to learn special functionality
  Risks automatically integrated into the project information:
    Not isolated in separate risk registers
    With no links between risks and the information they refer to
    Managed in the same workspace as all other information
  Access control, change control, baselines and reviews are available
    Applied in the same way as everything else
  Reports, metrics, KPIs, documents can immediately include risks
    No need to import/export or build tool interfaces or bridges

## Slide 19: Risk Profiles 6
Risk profiles show one or more risks on a horizontal time axis using the risks’ Start Date and End Date
Profiles can show line graphs against time of:
  Number of risks
  Total of risks’ values
  Total of each risk’s value weighted by its likelihood probability
Risk profiles can show stacked bar charts against time of:
  Numbers of each risk magnitude / priority / severity
  Total of risks’ values for each risk magnitude / priority / severity
  Total of risks’ values for each risk magnitude / priority / severity weighted by its likelihood probability
As for all other Cradle graphs, these profiles can be:
  Printed in a variety of formats and published in documents
  Exported as a data set for another tool, such as Excel

## Slide 20: Risk Profiles: 2
Risk counts for each risk priority against time
Total of the risks’ value (cost in this case), weighted by risk likelihood, against time

## Slide 21: RISK Licence 7
Cradle provides an optional Cradle-RISK module with a separate RISK licence
RISK licences are floating and dynamic, as are all other module licences
The RISK licence is used:
  When editing an item of the type defined to be a risk
  When generating a risk profile
Risk information can be defined and used in Cradle without the RISK module
The RISK module provides:
  Ability to define RAMs and RAM inheritance down a RBS
  Lookup of risk magnitude / priority / severity from a RAM
  Risk profiles
One RISK licence can be shared between 3 concurrent risk users

## Slide 22: Summary 8
  Cradle supports all aspects of a risk management plan
  Provides a RBS with any structure, any number of risk registers and risks
  Any number of RAMs with automatic inheritance down the RBS
  Full set of operations, including search, view, filter, edit, history, linking, traceability, coverage, reordering, adaptations, merge, split, find, replace, properties
  Risks can be captured from source documents
  Risks can be imported and exported
  Risks can be published in user defined reports and documents
  Provides full range of risk profile graphs
  Have user-defined workflows so can be reviewed, baselined and subject to formal change control through Cradle’s Configuration Management System (CMS)
  Available through the API and WSI